## Sheet1
Date | Xuemeng Wang (ProductOwner) | Deyu Yan (ScrumMaster) | Yuanhao Wang (Developer) | Mofei Wang (Developer) | Jiyuan Yang (Developer) | HengRui Huang (Developer) | Xingyu Fan (Developer)
Oct.1st | Decide what paltform we will use（JAVA+MySQL） | Deciede what user story we should finish at first sprint | Reserch for being familiar with the development environment (JAVA) | Reserch for being familiar with the development environment (JAVA) | Reserch for being familiar with the development environment (MySQL) | Reserch for being familiar with the development environment (Web) | Reserch for being familiar with the development environment (Web)
Oct.2nd | Summarize all user story and begin to research test | Schedule and record the meetings. Install and unified development environment | Install and unified development environment | Install and unified development environment | Install and unified development environment | Install and unified development environment | Install and unified development environment
Oct.3rd | Research the Farmwork of unit test. | Schedule and record the meetings. research the unit test. | Deal the environment problem and Discuss with Datebase designer. | Deal the environment problem and Discuss with Datebase designer. | Discuss with other member for designing the class of database | Design the main page UI and research the algorithm | Design the login page UI and research the algorithm
Oct.4th | Research and decide the Framework of unit test(). | Schedule and record the meetings. | Learing (!!) and Discuss with Datebase designer. | Learing (!!) and Discuss with Datebase designer. | Data analysis begins with the statement of data requirements . | Thinking about UI design and research the algorithm | Thinking about UI design and research the algorithm
Oct.5th | Begin to code test. | Check and ensure everyone's progress. Schedule and record the meetings. | Begin to code LogIn Function. | Begin to code Create Account function. | Begin to produces a conceptual data model. | Drawing the Sketches for design. Research the algorithm | Drawing the Sketches for design. Research the algorithm
Oct.8th | Check the user story and fix the mistake | Schedule and record the meetings. | Codeing LogIn Function and research the algorithm | Codeing create Account function and research the algorithm | Database design starts with a conceptual data model | Communicate with other teammates and modify the sketch with their | Communicate with other teammates and modify the sketch with their
Oct.9th | Check the user story and fix the mistake | Schedule and record the meetings. | Codeing LogIn Function. | Codeing create Account function. | Continue database design | Build the framework of the main page and login page | Build the framework of the main page and login page
Oct.10th | Continue code test. | Schedule and record the meetings. | Codeing LogIn Function, and discuss with the other developer | Codeing LogIn Function, and discuss the other developer | Developing an ER diagram | Read the backend code and disscus the algorithm | Read the backend code and disscus the algorithm
Oct.11th | Research the Farmwork of unit test again and code it. | Schedule and record the meetings and help product owner make test | Discuss the two different types of Account. | Discuss the two different types of Account. | Ensure the entries and attributes of the ER diagram | Build the framework of the login and registration page. | Build the framework of the login and registration page.
Oct.12th | Research the Farmwork of unit test again and code it. | Checkeveryone's progress, and change their work. Schedule and record the meetings. | Begin to integrate frontend and backend | Begin to integrate frontend and backend | Make sure database to be created according to the definitions we have produced. | Complete the login and registration page | Complete the login and registration page
Oct.15th | Updated and renew the user story, according to everyone's progress | Schedule and record the meetings | Deal the environment problem | Deal the environment problem | Deal the environment problem | Deal the environment problem | Deal the environment problem
Oct.16th | Prepar for sprint1 interview | Prepar the unit test (Discuss with Developer). Schedule and record the meetings | Fix Bug for the login function | Helping fix bug for other teammates | Read other's code | Communicate with backend teammates and fix the mistake | Communicate with backend teammates and fix the mistake
Oct.17th | Prepar for sprint1 interview | Prepar the unit test (code). Schedule and record the meetings | Reimplement the algorithm and change some require | Implament the restaurant registion and custmer registion | Test the database. | Fix the login and registration page bug. Connect to the database. | Fix the login and registration page bug. Connect to database.
Oct.18th | Prepar for sprint1 Review | Did unit test. Schedule and record the meetings. | Feed fake data for testing all the function we have. | Feed fake data for testing all the function we have. | Test the database and make some mandatory changes. | Read other's code | Read other's code
Oct.19th | Prepar for sprint1 Review and report | Did unit test. Schedule and record the Sprint Retrospective meetings. | Read other's code | Read other's code | Read other's code | Read other's code | Read other's code

## Sheet2
Date | Yuanhao Wang (ProductOwner) | Jiyuan Yang (ScrumMaster) | Xuemeng Wang (Developer) | Mofei Wang (Developer) | Deyu Yan (Developer) | HengRui Huang (Developer) | Xingyu Fan (Developer)
Oct.22nd | Decide what user stories should be done during sprint2 and begin test | Deciede what user story we should finish in the second sprint. | Begin to implement making reservation function. | Begin to implement confirming reservation function. | Design the sending notification page UI and research the algorithm | Design the making reservation page UI and research the algorithm | Design the confirming reservation page UI and research the algorithm
Oct.23rd | Begin unit test. | Schedule and record the daily scrum meetings. Check the unit test. | Continue implementing making reservation function. | Continue implementing confirming reservation function. | Thinking about UI design and research the algorithm | Thinking about UI design and research the algorithm | Thinking about UI design and research the algorithm
Oct.24th | Check user stories and begin coding. | Schedule and record the daily scrum meetings. Check everyone's status and offer help. | Continue implementing making reservation function and discuss with other developers. | Continue implementing confirming reservation function and discuss with other developers. | Drawing the Sketches for design. Research the algorithm | Drawing the Sketches for design. Research the algorithm | Drawing the Sketches for design. Research the algorithm
Oct.25th | Debug and unit test | Schedule and record the daily scrum meetings. Check everyone's status and offer help. | Discuss the three different acounts. | Discuss the three different acounts. | Communicate with other teammates and modify the sketch with their | Communicate with other teammates and modify the sketch with their | Communicate with other teammates and modify the sketch with their
Oct.26th | Check user stories and continue coding. | Check all the members' progress and reallocate their work. | Begin to integrate frontend and backend | Begin to integrate frontend and backend | Build the framework of the main page and login page | Build the framework of the main page and login page | Build the framework of the main page and login page
Oct.29th | Debug and unit test | Schedule and record the daliy scrum meetings. Check everyone's status and offer help. | Deal the environment problem | Deal the environment problem | Read the backend code and disscus the algorithm | Read the backend code and disscus the algorithm | Read the backend code and disscus the algorithm
Oct.30th | Check everyone's progress. | Schedule and record the daliy scrum meetings. Check everyone's status and offer help. | Fix Bug for the making reservation function | Fix Bug for the confirming reservation function | Build the framework of the login and registration page. | Build the framework of the login and registration page. | Build the framework of the login and registration page.
Nov.1st | Check user stories and continue coding. | Check all the members' progress and reallocate their work. | Begin to implement sending notification function. | Begin to implement sending notification function. | Complete the sending notification page | Complete the making reservation and confirming page | Complete the confirming reservation and confirming page
Nov.2nd | Debug and unit test | Schedule and record the daily scrum meetings. Check everyone's status and offer help. | Continue implementing sending notification function. | Continue implementing sending notification function. | Deal the environment problem | Deal the environment problem | Deal the environment problem
Nov.3rd | Check user stories and continue coding. | Schedule and record the daily scrum meetings. Check everyone's status and offer help. | Continue implementing sending notification function and discuss with other developers. | Continue implementing sending notification function and discuss with other developers. | Communicate with backend teammates and fix the mistake | Communicate with backend teammates and fix the mistake | Communicate with backend teammates and fix the mistake
Nov.5th | Unit test and renew user stories. | Schedule and record the daily scrum meetings. Check the unit test. | Discuss the three different acounts. | Discuss the three different acounts. | Fix the login and registration page bug. Connect to the database. | Fix the login and registration page bug. Connect to the database. | Fix the login and registration page bug. Connect to the database.
Nov.7th | Prepare sprint2 interview. | Prepare the unit test (Discuss with Developer). Schedule and record the meetings | Begin to integrate frontend and backend | Begin to integrate frontend and backend | Begin to integrate frontend and backend | Begin to integrate frontend and backend | Begin to integrate frontend and backend
Nov.8th | Prepare sprint2 interview. | Prepare the unit test (code). Schedule and record the meetings | Deal the environment problem | Deal the environment problem | Deal the environment problem | Deal the environment problem | Deal the environment problem
Nov.9th | Prepare sprint2 review. | Do unit test. Schedule and record the meetings. | Fix Bug for the sending notification function | Fix Bug for the sending notification function | Fix Bug for the sending notification function | Fix Bug for the sending notification function | Fix Bug for the sending notification function
Nov.10th | Prepare sprint2 review and report. | Do unit test. Schedule and record the Sprint Retrospective meetings. | Read other's code | Read other's code | Read other's code | Read other's code | Read other's code