## Sprint1
What we did now | what problem we have | How to fix it | What we will do for next sprint
We create a login page and completed it | Everyone has the different programming environment and style | Unify the environment and use more time to work together on Thursday and Thursday. It is onvenient for all members to communicate | Complete Customer interface, let user can view the restaurant that has been booked,
We use a simple way to create two different type of Account, omitted more button and interface | In Login page, there are too few prompts for users and their display time is too short | Add more hints and use more vivid colors | Complete restaurant interface. The interface will display the reserved customers and can agree or cancel.
We designed a simple Customer page and laid out the framework for the follow-up function. | The Home page lacks the logout function | Will be added in the function of "Me" | Let restaurant can interact with customers. The customer can get a reminder when the restaurant agrees or refuses
| The login interface is too direct and makes the user uncomfortable | Add another small homepage before the Login function. | Try to add find the restaurant function.
Improve UI

## Sprint2
What we did now | what problem we have | How to fix it | What we will do for next sprint
We implement the making reservation function. | In the login the registration page, the password is no hiding. | We will hide the password when the user input it. | Complete the function of modifying the restaurant information.
We implement the confirming reservation function. | There's scroll button to view the message and restaurant easily. | We will add pages and switching pages function. | Try to ddd the function of cancelling order.
We implement the sending notification function. | The information on the making reservation page is not detail enough. | We will add more information on our pages. | Improve UI
We create three different types of accounts, which include customer, owner and admin. | The notification form is too small and not clear. Also need a double check. | We will give the user more time to consider their reservation